## Completed FY24-25
Completed CIPs
FY 24/25
[5 empty] | Project Start Date |  |  | Construction Completion Date
Project | Project Number | Project Manager | Scope | Phase |  | Start | End |  | Status
FY2022/23 Annual Residential Pavement Rehabilitation | 24543 | Artin Megerdichian | Year 2 of 5 of the new residential pavement program to achieve a Citywide pavement condition index (PCI) of 73 by FY 2030-31. FY 2022-23 will perform grind and overlay on streets in poor and below condition primarily in sections 5,6,7, and 8. Project includes alleys. |  | 2023-11-23 |  |  | 2024-07-24
Larry Maxam Memorial Park Restroom/Building Renovation | 22756 | David Null | Renovation to improve functionality, meet current codes, and T-24 regulations. New scope includes a roof, seismic reinforcements, domestic water, sanitary sewer, & fire suppression systems, energy efficient windows and lighting, interior finishes, cabinetry, high-efficiency plumbing fixtures, toilet accessories, and stall partitions, internet service, and low-voltage networking equipment. Exterior improvements - selective facade and covered main entry, signage, concrete flatwork and system drainage, system upgrades for access control and security. | Construction | 2023-04-23 | 2023-04-23 | 2024-04-19 | June 2024 | Completed. Take off this list per Ken.
McCambridge Park Pool Repair | 24201 | Dean Pearson | The repairs included in this project are designed and engineered to strategically extend the operation of the Pool approximately 5 years until a planned replacement and/or modernization can be completed. The scope of the project has been developed to meet the Parks and Recreation Department's programming needs and the operation and maintenance requirements of Public Works. The project generally includes the repair of surface cracks in the pool, pool painting, reducing pool lanes by one lane, and replacement of selective mechanical and electrical components. The completed project will meet County Health - Recreational Waters guidelines. | Construction | 2023-07-21 |  | 2024-05-01 | 2024-05-01 | Project completed and opened on schedule in May 2024. Punchlist and project close-out in August.
DeBell Golf Course – Club House Improvements | 24221 | Dena Moon | Remove wall and sliding doors that divide the meeting room from the banquet space and replace them with a glass folding divider. This project will also make improvements to the two additional rooms that are generally used for weddings and other special events. | Design-Build | 2023-04-22 | 2022-04-22 | 2024-12-23 | 2024-06-24 | Completed June 2024.
Picnic Facility Improvements at McCambridge Park | 24817 | Mike Del Campo | Add new picnic benches and shade structure(s) to outdoor picnic area by tennis courts at McCambridge Park. |  | 2023-07-23 |  | 2024-07-24 | 2024-08-24 | Completed August 2024.
Police/Fire Evidence Storage | 23023 | Dean Pearson | This project will capitalize on existing, unused storage area (mezzanine/equipment area) within the Police/Fire Headquarters, and will design, engineer, and construct lightweight and secure storage areas to move Police evidence materials to the Police/Fire Headquarters. This project will provide more space for Public Works at the City Yard and create a convenient and appropriate storage area for Police evidence. | Construction | 2024-07-18 | 2022-05-22 | 2024-03-24 | 2024-07-01 | The project infrastructure work is complete. Relocation of contents with PD to be completed August - October.
Valley Park Ballfield Shade Structures | 24818 | Diego Cevallos | Installation of cantilever bleacher shade structure at Valley Park Ballfield. Includes design, engineering calculations, site plans, manufacturing of structure, project management, and installation of a shade structure over aluminum bleachers for program participants, employees, and the community. Parks will coordinate structure locations with PW and will be plan checked and permitted by CDD/Building division. Completed 8/29/24. | Design | 2023-07-23 | 2024-07-01 | 2025-08-01 | 2024-08-24 | Construction will begin on 8/19/24 with completion date on 8/26/24. Completed 8/29/2024.
FY2022/23 Annual Sidewalk Rehabilitation | 24542 | Frank Nerthling / Sevak Hakobyan | Remove and reconstruct damaged curbs, gutters, sidewalks, driveways, and pedestrian ramps in Zones 15, 16, 17, and 18; on the hillside west of Amherst. | Construction | 2023-07-22 | 2024-05-01 | 2024-10-01 | 2024-10-24 | Construction activities for this project have been completed.
Maple Street Park Playground Replacement | 24977 | Mike del Campo | Installation of new wide range inclusive and adaptive play equipment. | Planning | 2024-07-24 | 2024-10-24 | 2024-03-25 | 2024-11-24 | Completed November 2024.
Rogers Place Landscaping Project | 21712 | Frank Nerthling | This project will construct landscaping and aesthetic treatments for the Empire Interchange to discourage graffiti and improve aesthetics. Local funds identified in this project are reimbursed by Metro (Project Task 2). | Bid |  | 2023-09-22 | 2024-11-01 | 2025-01-25 | Construction for the project is complete. 90-days Plant Establishment period started October 17th.
McCambridge Park Playground Replacement | 24816 | Mike del Campo | Installation of new wide range inclusive and adaptive play equipment. |  | 2024-07-24 |  |  | 2025-02-14
Police/Fire Headquarters Flooring | 21305 | Anna Hartounian | Flooring replacement in multiple phases. | Construction Phase III | 2023-07-14 | 2023-10-02 | 2025-02-03 | 2025-02-25 | Phase 3 of this project commenced in mid-October and construction is Completed.
Note on K8: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Check year for anticipated "to start date." Is it Summer 2024?

## Completed FY23-24 (hidden)
Completed CIPs
FY 23/24
[6 empty] | Created in Oracle | Phase Schedule
| Project | Project Number | Project Manager | Scope | Phase | Project Start Date | Start | End | Construction Completion Date | Status
1 | Picnic Facility Improvements at Verdugo Park | 24214 | Mike Del Campo | Add new shade structure(s) to outdoor picnic areas to enhance the visitor's experience and provide increased safety from harmful ultraviolet (UV) radiation. Shade structures have the potential to generate additional revenue through permitted group gatherings and rentals. The Parks and Recreation Board has identified this project as a top priority. Additionally, the Department recently completed a series of community engagement workshops to determine the City's parks/facility needs where this was identified as a need by the community. Over 750 picnic facility reservations are scheduled each year. | Design | 2021-07-01 | 2023-07-21 | 2023-06-23 |  | Project Completed, June 2023
2 | DeBell Irrigation Improvements | 23859 | Mike Del Campo | Abandon in place all current irrigation and replace with modern updated water efficient irrigation using recycled water. | Construction | March 1 2022 | 2023-03-22 | 2023-08-22 |  | Project Completed, June 2023
3 | Whitnall Highway Park Fitness Equipment | 24563 | Mike Del Campo | Replacement of outdated fitness equipment at Whitnall Highway Park South. | Design-Build | 2022-12-01 | 2023-12-22 | 2023-05-23 |  | Project completed, May 2023.
4 | Police HQ/Fire 11 HVAC Retrofit and Repair | 23022 | Dean Pearson | This project will include system design, engineering, and construction. Funding will allow the replacement of some equipment to extend the service life of the HVAC equipment until the larger overall replacement project can be funded. | Construction | 2018-07-01 | 2023-05-22 | 2023-06-23 |  | COMPLETED and closing out.
5 | DeBell Golf Course Annual Improvements | 24561 | Mike Del Campo | Annual DeBell Golf Course improvements are required to maintain safe facility grounds while enhancing the quality of community recreation. Improvements include, but are not limited to: sand bunker renovation, course netting replacement, tree removal, tee level/widening, irrigation improvements, replacement of dirt cart paths to concrete, and the removal and replacement of netting at the driving range and perimeter of Golf Course. These improvements are necessary to increase the safety of players and overall community. Maintaining a safe and attractive facility for visitors and players is vital to the continued success of the DeBell Golf Course operations. Projects are outlined in a five year capital improvement program, and will occur in a phased plan approach. | On-Going | 2022-07-01 | 2023-07-22 | 2023-06-23 |  | Project Completed.
6 | Animal Shelter Shade Structure | 24562 | Kris Smith | This project will provide a new outside shade structure for Burbank Animal Shelter and shade covering for 50 kennels. | Design-Build | 2022-08-01 | 2023-08-22 | 2023-07-23 |  | Projected completed. August 2023.
7 | DeBell Irrigation Improvements | 23859 | Mike Del Campo | Abandon in place all current irrigation and replace with modern updated water efficient irrigation using recycled water. | Construction | March 1 2022 | 2023-03-22 | 2023-08-22 |  | Project Completed, June 2023
8 | Verdugo Aquatic Facility Public Art | 23432 | Paula Ohan | Funds will be used to develop a public mural for the Verdugo Aquatic Facility. | Design | 2023-07-19 | 2023-10-22 | 2023-12-22 |  | Project Completed, December 2022. However, the artist is adding a design element to include the newly added Sister City.
9 | Fiscal Year 21-22 Annual Arterial Pavement Rehabilitation | 24185 | Diana Reznik | The project will improve Victory Blvd from Clybourn Ave to Buena Vista St, San Fernando Road from south of Hollywood Way to north of Buena Vista St, and resurface the Burbank Fire Department Training Center parking lot. | Construction | 2023-07-21 | 2023-04-22 | 2023-07-23 |  | Waiting for two Change Orders to be approved to pay invoices and close project.
10 | Alameda Signal Synchronization | 23457 | David Wilcox | This project will synchronize 20 traffic signals on Alameda between Buena Vista and Glenoaks and on Riverside between Buena Vista and Chavez. The project is 100 percent funded by Metro Measure R Highway funds. | Design | 2023-02-20 | 2023-06-20 | 2023-06-23 |  | Design complete. Construction to occur with I-5 Project below.
11 | McCambridge 1 Ballfield Bleacher Shade Structure | 24556 | Diego Cevallos | Installation of cantilever ballfield bleacher shade structure at McCambridge softball field 1. Work to include design, engineering calculations, manufacturing of structure, and installation of a sheltered area over aluminum bleachers for program participants, employees, and the community to enjoy. | Design-Build | 2023-08-22 | 2023-08-22 | 2023-08-23 |  | Project Completed, October 2023.
12 | Park Playground Equipment and Replacement Valley and Ovrom Parks | 24213 | Mike Del Campo | New playgrounds/fitness equipment was the second highest prioritized project identified by the community. Playgrounds are an essential commodity in neighborhood parks and it is important to maintain the playgrounds to ensure longevity and safety. The Department keeps track of the installation dates of playgrounds to ensure that they are kept on a replacement cycle plan. Valley Park will receive a playground equipment replacement and installation of a new shade structure. The playground equipment and shade fabric at Ovrom Park will be replaced. | Design | 2023-07-21 | 2023-07-21 | 2023-11-23 |  | Construction at Ovrom Playground was completed June 2023. Construction at Valley Park Playground is anticipated to start September 2023 and is expected to be completed by November 2023. Valley Park Playground Construction began on August 30, 2023 and expected to be completed on October 20, 2023.
13 | Verdugo Water Slides | 24560 | Diego Cevallos | Application of gel coating of interior and exterior of two water slides. | Design-Build | 2023-07-22 | 2022-07-22 | 2023-08-23 |  | Project complete, will move to Completed tab. The work was anticipated to be completed by May 2023 in preparation for the summer 2023 season, but due to heavy rains this project was delayed. Project will start and be completed in August 2023 during the annual maintenance closure period. The PO was issued. This project will be completed December 2023.
14 | Ballfield Lighting Modernization at McCambridge 1 & 2 | 24557 | Mike Del Campo Diego Cevallos | Modernize ballfield lighting with energy efficient light emitting diode (LED) systems at McCambridge Fields 1 and 2. The existing eleven (11) light standards will also be replaced. The scope will include pre-cast concrete bases with integrated lighting grounding and light poles. | Design-Build | 2023-02-23 | 2023-02-23 | 2024-02-23 |  | P&R and PW are coordinated efforts on the project. The design has been completed. This Project started on December 4th. Ballfield #2 has been completed. Musco began work on ballfield #1 on January 8th. Construction was completed on February 7, 2024. A light survey was completed on February 12, 2024. NOC will be submitted after P&R and PW meet to closeout the project. Project is complete.
15 | Downtown San Fernando Blvd Reconfiguration (Phase 1) | 24206 | Edward Yu | This project reconfigures San Fernando Boulevard in Downtown Burbank to implement one lane of one-way traffic northbound, install signage, and modify roadway signal and striping, reconfigure parking, and add additional outdoor dining opportunities. If successful, a phase two project could be implemented to construct a long-term improvement with permanent wide sidewalks and traffic calming. | Phase 1 Complete | 2023-07-21 | 2024-02-24 | 2024-03-24 | 2024-03-24 | Phase 1 complete on March 8, 2024 . Conducting observations and evaluations of pilot program. Phase 2 will be created as a new project.
16 | Front St. Cycle Track Bike & Pedestrian Minor Project Improvements | 22377 | Vikki Davtian | The City's Bicycle Master Plan identifies a missing top priority safe bicycle connection from the Downtown Burbank Metrolink station to the Downtown Area. This project will design and construct approximately a half-mile protected Class IV bikeway along Front Street from the Downtown Burbank Metrolink station to Verdugo Avenue and South Ikea Way. This project is funded by Transportation Development Act (TDA) Article 3 and Measure R Local Return funds. | Construction | 2023-02-16 | 2024-03-31 | 2024-06-06 | 2024-05-24 | Project is complete.
17 | Schafer Ballfield Bleacher Shade Structure Installation | 24210 | Diego Cevallos | Installation of wrap around cantilever ballfield bleacher shade structure at Schafer field. Restricted BAF funds will be allocated to partially cover the costs of this project. | Construction | 2023-10-22 | 2022-10-22 | 2024-03-22 |  | Project completed, May 2024.
18 | McCambridge Recreation Center Gym Mural | 23433 | Megan Wilke | Funds will be used to develop a public mural for the McCambridge Recreation Center gymnasium. | Construction | 2023-07-19 | 2019-07-19 | 2024-05-01 | 2024-07-01 | Mural completed on May 10, 2024. Identification Plaque is in production.
19 | FY 23/24 Storm Drain Pump Station and Catch Basin Upgrades | 21310 | Steve Walker | This is a multi-year project is to implement capital improvements to the City's storm drain pump stations and catch basins/connector pipes, and related facilities. This project will improve the condition of storm drain facilities, thereby increasing the system reliability and reducing the chance of flooding during significant rain events. | Design/ Construct |  | 2023-07-01 | 2024-06-01 | 2024-06-01 | In FY 2023-24, new valves were installed and ventilation improvements were made at the Victory Place Storm Drain Pump Station; and a new sump pump and starter equipment was installed and pump motors were rehabilitated at the at the Hollywood Way & San Fernando Storm Drain Pump Station. In addition, the emergency project to remove and replace the deteriorated storm drain pipeline adjacent to the property at 5 West Magnolia Blvd. (Swaner Hardwood) was completed.