## PW CDD FY23-24
Public Works and CDD CIPs
February 2025
[6 empty] | Created in Oracle | Phase Schedule
| Project | Project Number | Project Manager | Scope | Phase | Project Start Date | Start | End | Estimated Construction Completion Date | Status
1 | Boys & Girls Club 2244 N. Buena Vista Building Improvements | 24747 | Anna Hartounian | The 1949 building requires modernization including seismic strengthening, upgrading building utilities, ADA compliance, Fire Life Safety, and tenant improvements to accommodate current programming. | Planning | 2023-02-23 | 2023-10-23 | 2024-02-01 | 11/25/2024 2026 | Design kick off meeting 6/27 concluded. The design is managed by CDD. Entitlements to be completed by January 2025. Out to bid between February - August 2025. Construction will take place in 2025 and completed in 2026. | Cont'd
2 | F-104D Starfighter Aircraft | 24566 | Anna Hartounian | Rehabilitate the F-104D Starfighter Aircraft at George Izay Park. Design in 23/24, construction in 24/25. | Design | 2023-07-23 | 2023-01-23 | 2024-06-01 | 2025-03-25 | A co-op contract is being processed. Construction to start in Feb. and be completed by Memorial Day in May 2025. | Cont'd
3 | Fire Station 11 Kitchen Modernization | 24824 | Anna Hartounian | Comprehensive modernization of existing 25-year-old kitchen: repair and replace cabinets, counters, appliances, and lighting, replace existing interior finishes, and selective furnishings. | Design | 2023-06-16 | 2024-05-24 | Feb-25 | Fall-26 | Design is schedule to be completed in March 2025. Buildin permit plancheck will start in April and be completed in June 2025. Construction will start in summer 2025 with a Co-op agreement and be completed in Dec. 2025. | Cont'd
4 | FY2022/23 Annual Arterial Pavement Rehabilitation | 24541 | Frank Nerthling | The arterial pavement program continues to address major and secondary arterials and collector roadways rated poor and below condition to achieve a Citywide pavement condition index (PCI) of 73 by FY 2030-31. Combined with residential pavement program Public Works expects to achieve a citywide PCI of 73 by FY 2030-31. Project includes alleys. | Design | 2023-07-22 | 2022-07-22 | 2024-05-01 | 3/24/2025 6/2025 | Went to City Council on Dec. 10th and awarded the contract to Hardy & Harper Inc. Had Pre-Construction Meeting on February 5th. Will begin construction in Mid-March. The project will improve Victory Blvd (Providencia Ave to the City Limits), and Alameda Ave (Lima St to California St). | Cont'd
5 | FY2023/24 Annual Arterial Pavement Rehabilitation | 24812 | Frank Nerthling | The arterial pavement program continues to address major and secondary arterials and collector roadways rated poor and below condition to achieve a Citywide pavement condition index (PCI) of 73 by FY 2030-31. Combined with residential pavement program Public Works expects to achieve a citywide PCI of 73 by FY 2030-31. Project includes alleys. | Design | 2023-07-18 | 2024-01-24 | 2024-12-24 | 2025-10-25 | Have determined the next arterial street Hollywood Way (from Victory Blvd to Vanowen St), working on PS&E and will determine the estimated cost to improve these segments. Design 35% completed. | Cont'd
6 | FY2023/24 Annual Residential Pavement Rehabilitation | 24820 | Artin Megerdichian / Frank Nerthling | Year 3 of 5 of the new residential pavement program to achieve a Citywide pavement condition index (PCI) of 73 by FY 2030-31. FY 2023-24 will perform grind and overlay on streets in poor and below condition primarily in sections 15, 16, 17, and 18. Project includes alleys. | Design | 2023-07-14 | 2023-08-23 | 2024-07-23 | 2025-09-24 | PS&E 95% completed. | Cont'd
7 | FY2023/24 Annual Sidewalk Rehabilitation | 24811 | Artin Megerdichian / Sevak Hakobyan | Remove and reconstruct damaged curbs, gutters, sidewalks, driveways, and pedestrian ramps in Zones 13 and 14. | Design | 2023-06-14 | 2024-11-24 | 2024-08-24 | 10/24/2025 6/2026 | Design 65% completed. | Cont'd
8 | Olive and Magnolia Safety Bridge Railing Replacements | 24203 | Artin Megerdichian | These bridges were built in the 1950s with barrier railings at a height of 39". These barrier railings are currently substandard and carry hundreds of pedestrians daily across the bridges. The Olive bridge has the most foot traffic due to the vertical connection to the Metrolink station. The Magnolia bridge currently has development projects underway on either end and should see a significant increase in pedestrian traffic once the projects are complete. | Design | 2023-03-21 | 2023-12-23 | 2024-12-23 | June 2026 | Working with Stantec and Caltrans teams to determine acceptable railing options, and then bring options before DOC and IOB for feedback. | Cont'd
9 | Vehicle Lift Equipment Modernization | 24547 | Jose Rodriguez/ Sevak Hakobyan | Complete modernization of fourteen (14) vehicle lifts to accommodate current Fleet requirements including all City light and heavy duty vehicles. Project includes design, engineering for lift modernization. The scope of the project will also include hazardous materials mitigation, which includes soils testing. | Design | 2023-07-22 | 2024-09-25 |  | FY 31/32 | Project will be divided into phases and have a month and year for the first one or two to be done. Pacific Lift (equipment contractor) will present design plans and project estimate by next month for review. Status: Project will be divided into 6 phases, Phase one and two will replace all light duty and meduim duty lifts (total of 7 lifts), Phase 3-6 will be the replacement of Heavy duty lifts.
10 | Chandler Bikeway Extension | 22702 | David Kriske/David Null | Project will extend the Chandler Bikeway from its current eastern terminus at Chandler Boulevard and Mariposa Street to the future San Fernando Bikeway along the Western Burbank Channel. The completion of this project will help to close the gap between two regionally significant Class I bikeways and will provide pedestrian and bicycle connectivity to the City's Downtown Metrolink station. | Design | 2023-02-17 | 2025-01-25 | 2025-12-25 | Spring 2028 | Retained Kimley Horn & Associates for PS&E out for Evaluation, 30 % Design Mid-2025, 90% Design PS&E by Late 2025, Bid Construction start by Mid 2026. | Cont'd
11 | San Fernando Bikeway | 19056 | David Kriske/David Null | Class I bike path that will be constructed along San Fernando Boulevard, Victory Place, and the Burbank Western Channel between Cohassett Street and the Downtown Metrolink station. This project completes the final three miles in a 12-mile regional bike path. Most of this project's costs are funded by a Metro Call for Projects grant. This project is a top priority project on the Bicycle Master Plan. | Design | 2023-07-09 | 2020-08-20 | 2025-03-25 | Fall 2026 | 100% Plans under Review. Construction by Early 2026. | Cont'd
12 | CSB Security Enhancements | 24375 | David Null | Install barrier to stairway at ground level, activate code for elevator use, install full height doors to staff areas (4), and install screening for 2nd floor railing system. | Pre-Con |  |  | 2024-04-24 | July 2025 | Project will begin with submittals January. Demolition will start in April after custom materials manufactured and approved. Construction in CSB April, May, June, July 2025. | Cont'd
13 | Orange Grove Parking Structure Restoration and Repair | 22365 | David Null | This project includes repair of the delaminated exterior plaster, stairs, and painting of the entire parking structure exterior at the Orange Grove parking structure. The wall and stair repairs are necessary to correct structural deficiencies and the paint will help preserve the infrastructure of the parking facility. | Design | 2023-06-16 | 2020-03-20 | 2025-04-11 | 2026-06-01 | Final maintenance design being refreshed with consultant and Parking Authority. | Cont'd
14 | City Building Seismic Retrofit and Gross Park Facility Improvements | 23021 | David Null | This project will fund the construction and mandatory seismic retrofit the following buildings: DeBell Driving Range, DeBell Golf Maintenance Building, and Robert Gross Park Exercise Building. It will also modernize the Robert Gross Park Exercise Building's infrastructure, and includes ADA and fire sprinklers/monitoring code required modernization. | Design | 2023-07-18 | 2020-07-20 | TBD | TBD | Project was recently reassigned to David Null. Design is currently complete to approximately 90% (not including Bid Spec). Staff reengaged architect to complete design and include additional scope to address fire, life, safety improvements. Design will go through plan check at 100%. | Cont'd
15 | Victory Blvd and Buena Vista St Signal Synchronization | 23780 | David Wilcox | Project will collect data and analyze the synchronization of 24 traffic signals on Victory Blvd between Buena Vista and Alameda and on Buena Vista St between Interstate 5 and Glenoaks Blvd. Traffic signal controllers, electrical service, cameras, and wiring will be upgraded at 3 locations. Design will include data collection/analysis, signal timing adjustments, and procurement of traffic signal upgrade equipment. Project construction includes signal equipment upgrades to 3 intersections. | Design |  | 2025-03-01 | 2025-10-01 | 6/13/2025 Dec-26 | Staff is working on the RFP and will issue by February 2025. Consultant will be on-board by March 2025 with the Design phase beginning in May 2025. The anticipated completion date of the project is December 2026.
16 | City Hall Fountain Restoration and Modernization | 24827 | Dean Pearson | Pop-up project due to new drought laws. Restore the existing historic fountain, including gutting and replacing pertinent MEP infrastructure to accommodate recycled water with sustainability benefits such as improving performance while reducing energy consumption. | Construction | 2024-09-24 | 2024-02-23 | 2025-06-05 | 2025-07-01 | Bid package advertised in January, however no bids were received. Staff is developing a new timeline to rebid the project. Construction estimated April 2025 to July 2025. | Cont'd
17 | City Yard Services Building (CYSB) | 21739 | Damian/Lifan | Project replaces existing 1962 Building Maintenance Parks Storage Facility and site infrastructure improvements for future utility connections. New 11,000+ s.f. facility includes employee locker/changing areas, a multi-purpose room, restrooms, materials/equipment storage, and computer work stations. On-site/off-site improvements include all new utilities and related infrastructure, stormwater management system, fiber/data/security, ingress/egress re-alignment, and partial campus perimeter security fencing. | Pre- Construction | 2023-07-15 | 2024-09-23 | 2025-02-25 | 2026-10-26 | Working with Procurement and CAO to create new RFQ/RFP/CMAR with GMP Agreement for project (as well as six bid specifications templates). Estimated to Advertise for RFI in July 2025 and RFP for Pre Construction Services/CMAR in Sep. 2025; Construction to start in Aug.2026 and be completed by Nov. 2027. | Cont'd
18 | Downtown Burbank Metrolink Station Waterproofing and Elevator Modernization | 21272 | Dean Pearson | This project will restore the waterproofing system and modernize the elevator's systems, equipment, fixtures, and cab interior finishes; code-compliant upgrades for fire/life/safety, elevator machine room cooling. | Construction | 2023-06-13 | 2024-06-01 | 2025-04-01 | 4/25/2025 May-25 | Project was approved by Council on 3/26/24. Construction - NTP June 17, 2024 (290 days) - Construction completion May 2025. | Cont'd
19 | Exhaust System Modernization | 24893 | Dean Pearson | This project replaces specialized ventilation equipment that collects and expels diesel fumes, carbon monoxide, particulates, and other harmful airborne products occurring in fire stations and in vehicle repair shops, in PD/Fire HQ, PW Yard, and all Fire Stations. The work will include replacing leaking or inoperable ductwork, new magnetic connectors, rails, ductwork, and automatic controls. | Design | 2023-07-22 | 2022-07-22 | 2024-10-24 | May 25 July-25 Feb-26 | 90% Plans and Specs were completed submitted to Procurement for review. Advertise in March; Construction July 2025 - February 2026. Schedule variance to allow additional time to work together with Procurement to finalize bid documents. | Cont'd
20 | Fuel Systems Modernization | 23018 | Dean Pearson | This project includes terminal replacement and low voltage infrastructure necessary to support new software/hardware at all of the City's Fire Stations (Stations 11-16), as well as on the mobile pump unit on truck, which fuels equipment at the Landfill. This project will also include replacing tank monitoring equipment for more accurate reporting. | Design | 2023-06-18 | 2022-07-22 | 2024-10-24 | 7/25/2025 Nov-25 | Two out of nine fuel terminal card readers were replaced in December 2025, and one more reader will be completed by April 2025. Fuel system engineer to design needed mondernization of whole system from February - April 2025. Staff will pursue sole source justification for selected vendor from May to July . Construction is estimated to be completed November 2025. | Cont'd
21 | Jail Door Control System Modernization | 23049 | Dean Pearson | This project will replace and modernize the 24 year old legacy Jail locking system and components. The modernization will include the complete integration and installation of all electronics, software, hardware, casework and fixtures required to replace and modernize the existing system. | Design | 2023-07-18 | 2019-10-19 | 2024-10-23 | 8/1/2025 Mar-26 | Tech spec completed, finalizing full bid documents. Bid docs submitted to Procurement for review in October 2024. Advertise in April; construction estimated September 2025 - March 2026. Focused maintenance will be provided in the interim to ensure uninterrupted operation of this critical existing system.
22 | PD Jails Video Storage Upgrade | 24823 | Dean Pearson | Install new Video Manage System (VMS) equipped with sufficient storage to provide the required 1-year surveillance retention for the facility. | Construction | 2023-07-23 | 2024-07-24 | 2024-09-24 | 2/16/2025 Jun-25 | IT requested in August to cost compare two different integrators for surveillance storage systems to ensure we get the best price and future proofing. IT, PW and PD met in October to review the results and selected an integrator. A We're evaluating vendor was selected through a cooperative purchase agreement and contract documents are being produced. and anticpate a selection by February 2025. | Cont'd
23 | PD HQ Fire 11 Parking Area Waterproofing and Restoration | 24826 | Dean Pearson | Design/repair/restore waterproofing systems for the facility including, subterranean waterproofing, architectural planters, and all parking areas. Includes remediation of cracks and openings in concrete substrate and replacement of the parking area water proofing and drainage systems including expansion systems, closed cell foam compressible flashings, and engineered profiles. Due to the depth excavation required and disruptive construction impacts, a phased restoration will be done over the course of several years. | Design | 2023-07-23 |  |  | TBD Jun-26 | Preliminary design (testing, leak investigation) for scope refinement is 90% complete. Multi-phased project. Design started January 2025 with Phase 1 cosnstruction anticpated to start September 2025. | Cont'd
24 | Roof 1 - (Annual) Roof Restoration - Multiple Roofs (Parks, BWRP, and Animal Shelter) | 21472 | Dean Pearson | Roof repair and restoration for multiple roofs: Olive Recreation Center, Joslyn Adult Center, Creative Art Center, and the Pottery Building . WWTP offices and Animal Shelter as well. This will be the last year for this "annual" project. | Design | 2023-06-14 |  | 2024-10-23 | 9/1/2025 Dec-25 | New construction manager hired. project scope and bid documents with Consultant. Submit 90% plans and specs to Procurement in August 2024. Advertise: March February 2025 Construction : June 2025 - December 2025
25 | Roof 2- Recycle Center Warehouse Improvements - Roof Replacement | 21300 | Dean Pearson |  | Design |  | 2024-08-22 | 2024-10-23 | 8/1/2025 Jan-26 | New construction manager hired. Project scope and bid documents with Consultant. Submit 90% plans and specs to Procurement in November 2024. Advertise: April March 2025; Construction: July 2025 - January 2026
26 | Roof 3 - PD HQ Fire 11 -Roof and Structure Waterproofing | 24548 | Dean Pearson | This project will design, repair, and restore all water intrusion related deficiencies related to the roof, drain, and building envelope. The building envelope includes all vertical surfaces: windows, doors, architectural features/projections on the exterior of the building. | Design | 2023-07-22 | 2025-02-22 | 2025-02-24 | 2025-12-01 | Revalidate project scope and bid documents with Consultant. Submit 90% plans and specs to Procurement in December 2024 Advertise: April 2025 Construction: July 2025 - December 2025 | Cont'd
27 | Underground Storage Tank Replacement at Fire Stations 12 & 16 | 24546 | Dean Pearson | Replace existing underground 1,000 gallon un-leaded gasoline and diesel tanks at FS 12 and 16. | Design | 2023-01-23 | 2023-01-23 | 2024-08-23 | 5/1/2025 Nov-25 | UST at FS 12 and 16 were removed in June 2024. 90% Bid Docs for the permanent tank replacement were submitted to Procurement in May ; Advertise in March February 2025. Construction June 2025 - November 2025. A PO for the Procurement of temporary fuel tank system was issued.
28 | Main Street/Elm Avenue Intersection Improvement | 24739 | Edward Yu | Construct a pedestrian/equestrian crossing with warnings and signal lights consisting of rectangular rapid flashing beacons (RRFB) at the intersection. Other improvements will include ADA ramps and street lighting at the crossing. | Design |  | 2024-08-24 |  | Dec-25 | Task order has been issued and Iteris is working on the RRFB design, specifications, and estimates. Design is expected to be completed by end of November 2024. | Cont'd
29 | Downtown San Fernando Blvd Reconfiguration (Phase 2) | 24206 | Edward Yu/CDD | The scope of Phase 2 is dependent upon the response and data collection of Phase 1 which can result into two general options: 1) reverting back to the original condition or 2) constructing more long-term improvements with permanent sidewalk and curb extensions, modifications to traffic signal equipment, and additional traffic calming measures. | TBD |  | TBD | TBD | TBD | Phase 2 project is TBD based upon the response and data collection from Phase 1.
30 | Foy Park & Park Area Light & Lighting Infrastructure Modernization | 24825 | Jose Rodriguez | Validate current photometric requirements for the Parking Area and interconnected, adjacent Park Lighting. Design new lighting and replace required infrastructure. | Design | 2023-07-22 | Jul-25 |  | 2025-06-25 | Design to be completed in March 2025. Construction can start in April 2025 with a Co-op agreement and be completed June/July 2025.
31 | New Burbank Central Library - Civic Center | 24218 | Ken Berkman | Design and construction of a new 65,000 SF Library + ~20,000 SF of office space for ASB staff. ASB will be replaced with functional open space and the Wells Fargo building will also be demolished. | Pre-Design | 2023-07-21 | 2024-06-01 | 2027-02-01 | 2029-02-01 | PM Services RFP released 2.25. Proposals due 4/8. Council Award slated for 5/20. Completion of the Metrolink Downtown TOD Specific Plan and EIR will environmentally clear the project for design/build RFQ/P procurement.
32 | McCambridge Park Stormwater Capture Multi-Benefit Project | 24822 | Kenneth Kozovich | Includes improvements: an underground stormwater capture system (infiltration gallery), bioswales in two parking lots, planting of native trees, improved ADA paths, picnic tables with shade structures, fitness stations and a 9-hole disc golf course, led pedestrian and/or ballfield lighting throughout park, and solar power at the recreation center and basketball court. | Design |  | Jan-24 | Dec-26 | 2028-12-28 | Design consultant selection began in FY 2023-24 and will be completed in FY 2024-25. Preliminary design is scheduled to begin in Fall 2024, with 70% PS&E package scheduled to be completed in 2026 to go with new grant funding applications. Final design is scheduled to be completed in 2027. Construction is scheduled to be completed in December 2028.
33 | Homeless Solutions Center at 323 S. Front Street | 24970 | Simone | The development of a Homeless Solutions Center at 323-333 Front Street, its adjacent site at 10 East Verdugo, and the ability to use a small portion of the Metrolink Parking lot will continue the work toward developing a Homeless Solutions Center in the City and in return will help to eradicate homelessness through programs and services provided by the center. | Design |  |  |  | TBD | Community Development Department (CDD) staff has held various meetings with other City departments to receive input on the design to address ingress and egress concerns, existing utilities, and potential future development options for Permanent Supportive Housing. Projection is within the Council approved 5-year Homeless Plan.
34 | First Street Class IV Bike Lane | 23016 | Vikki Davtian | Design and construct approximately 0.8-mile protected Class IV bikeway on North First Street from North San Fernando Boulevard to East Verdugo Avenue. The project will also incorporate pavement improvements along the alignment where the pavement is in poor condition. | Design | 2023-07-18 | 2022-06-22 | 2024-12-30 | May-26 Dec-26 | Design is currently 90% complete. Design Phase to be completed in March 2025. Advertise in Jan 2026. Construction to start in June 2026 and complete construction by Dec 2026. Status: Staff preparing bid documents for the construction. | Cont'd
35 | Glenoaks Blvd. Arterial | 22690 | Vikki Davtian | Reconstruct 13 signals along Glenoaks Boulevard and 1 signal on First Street. This project is 100% funded by Metro Measure R Highway funds. | Construction | 2023-07-17 | 2022-11-22 | 2025-06-25 | Nov-24 Jan-25 | Construction complete in early January 2025. Pending final project close out.
36 | I-5 Arterial Phase 3 | 23779 | Vikki Davtian | Reconstruct four traffic signals: Victory/Elmwood, Magnolia/Reese, Magnolia/Mariposa, and Magnolia/Screenland. 100 percent funded by Metro Measure R Highway funds. Phase I (Design) was completed in June 2023 in the Alameda Signal Synchronization project (23457). This project is a continuation of the Alameda Synchro Project and is primarily for construction. | Construction | 2023-07-20 | 2025-07-01 | 2025-12-01 | Dec-25 June-26 | The design was completed as part of the MR310.55 Alameda Signal Sync Project. Project construction will start after the Glenoaks Project is complete. Advertise in July 2025. Construction is scheduled to begin in Nov 2025 and complete by June 2026. Status: Staff preparing bid documents for the construction. Material procurement in progress, material ETA August 2025.
Legend:
On schedule
3 months behind
4+ months behind

## Parks FY23-24
Parks CIPs
February 2025
[6 empty] | Created in Oracle | Schedule
| Project | Project Number | Project Manager | Scope | Phase | Project Start Date | Start | End | Estimated Construction Completion Date (From CIP Sheets) | Status
1 | Schafer Ballfield Lighting | 24813 | Diego Cevallos | Modernize ballfield lighting with energy-efficient Light Emitting Diode (LED) systems at Schafer Ballfield at Ralph Foy Park. | Design | 2023-07-23 | 2023-08-01 | 2025-01-01 | 2025-06-01 | Additional fund approved as part of FY 24-25 Budget. Council approved Co-op agmt. on 8/27/24. Performance and Payment Bonds, insurance, and all purchasing documents/requirements have been received from Musco. PO was issued October 2024. This project requires coordination with PWs and KSG on final design. Estimated construction completion date May-June 2025.
2 | Community Garden | 19540 | Diego Cevallos | Development of a 0.32-acre parcel (Chandler/Pass and Hollywood/Clark) into a community garden by community volunteers and donations. | Construction | 2023-07-15 | 2023-08-15 | 2024-11-23 | 2025-06-01 | In progress. The Chandler/Pass Community Garden opened in May 2022. On 8/15/23, LADWP received 100% Construction Documents for the Hollywood Way/Clark Community Garden. LADWP approved plans on 6/25/24. Fencing was completed on 9/24/2024. Final phase will include installation of irrigation lines, the buildout of the garden beds, and the purchase of a storage shed. Irrigation completed on 1/19/25. Ordered materials to start the volunteer garden bed build. Anticipating a "Grand Opening" on February 22, 2025.
3 | Olive Recreation Center Re-Design | 23468 | Diego Cevallos | The first phase is for the completion of draft schematic designs for the re-design of the Olive Recreation Centers. Phase 2 will include an aerial topographic and field survey, phasing feasibility studies, and a 3D rendering of the redesign. Project include offices, recreation classrooms, storage rooms, gymnasium, restrooms, a kitchen, and a stage. | Planning | 2023-07-19 | 2019-07-19 | 2024-06-24 | 1931-06-01 | In progress. Phase 1 - Public Engagement and completion of Master Plan Report. Completed in FY 2021-22. Phase 2 - Topographic Survey and 3-D Renderings, presented to the Council in December 2024, received approved. Presented to DOC on 10/14/2024. Park Board provide support for the 3D renderings and Architectural Analysis during 11/14/2024 board meeting. Phase 3 - Schematic design and design development in progress. PSA with Architects is being finalized. Engaging a Project Manager to represent the City in the CEQA and design development process.
4 | Mary Alvord Recreation Center Basketball Side Backboards Replacement | 24215 | Diego Cevallos | Replace four basketball side backboards at the Verdugo Recreation Center with four height adjustable backboards. Restricted BAF funds will be allocated to fully cover the costs of this project. | Design | 2023-12-21 | 2021-12-21 | 2024-12-01 | 2024-12-01 | P&R and PW Facilities completed the final design. Plan Check and Building permit process completed. Working with Purchasing and PWs to issue PO. Estimated construction start date August 2025.
5 | Animal Shelter Kennel Flooring | 24565 | Kris Smith | This project will provide the Burbank Animal Shelter installation of a new nonslip epoxy (or other) coating system to the existing flooring in the two kennel buildings including the main public walkways. Sept 2023 decided to not use epoxy, alternatives being considered. | Design | 2023-08-22 | 2022-08-22 | 6/30/20251/31/2511/30/25 | 2024-06-25 | P&R coordinated RFQ for the kennel flooring project. PW retained the services of LCDG to provide four options. After further review, options were not adequate for operations. PW identified an alternative product for consideration. PW and PR staff reviewed proposal, references and samples of materials. Shelter staff is testing the samples in the kennels. Product is not a viable option for Shelter operations. PW and PR have decided to repair and refinish the existing concrete flooring. LCDG is working on developing the job scope for the project, cost estimate, plans and drawings.
6 | Brace Canyon Park Ballfield | 23441 | Diego Cevallos | Replacement of living turf grass with artificial or natural turf. There is also a proposed rubberized running track around the perimeter of the ballfields. | Design | 2023-07-21 | 2021-07-21 | TBD | TBD | Environmental Review report author is no-longer with the firm. P&R working with a new Project Manager to complete the report. Presenting to DOC April 2025. Presenting to City Council Spring 2025 for approval/direction.
7 | Dick Clark Dog Park | 24253 | Mike Del Campo | Preserve and expand open space at Johnny Carson park to develop an off-leash dog park to promote exercise and wellness for dogs and their owners. | Construction |  |  | 2025-05-01 | 2024-12-24 | Informational community meetings were held on March 2 and 6, 2024. Consultant is finalizing Construction Documents. 1/6/25 - Received LADWP's second round of feedback. Resubmitted for final approval on 1/6/25. Will take to IDRC once construction plans are approved by LA. Anticipated completion date is Summer 2025.
8 | Irrigation - Foy Irrigation Replacement | 24814 | Mike Del Campo | New irrigation system to work with existing smart controllers. The Parks and Recreation Board supported this project at the November 10, 2022 meeting. | Design | 2023-07-23 |  | 2024-09-01 | 2025-06-01 | Design completed.
9 | Irrigation - Izay Irrigation Improvements | 23858 | Mike Del Campo | Upgrade the irrigation system at George Izay Park. | Construction |  | 2022-11-22 | 2024-09-23 | 2025-06-25 | Bid posted for solicitation on 11/13/24 and closed on 1/22/25. Pending Purchasing review of bids for responsiveness.
10 | Irrigation - Maxam Memorial Park Irrigation Replacement | 24815 | Mike Del Campo | Upgrade the irrigation system at Larry L. Maxam Memorial Park. | Design | 2023-07-23 | 2023-07-01 | 2024-09-01 | 2025-06-01 | Design completed.
11 | Irrigation - McCambridge Irrigation Replacement | 24559 | Mike Del Campo | Upgrade of the irrigation system at McCambridge Park. | Construction | 2023-08-22 | 2022-08-22 | 2024-11-22 | 2025-06-25 | Design is complete. Construction funding was approved as part of the FY 23/24 Budget Process. P&R is waiting for Izay Irrigation Project.
12 | Santa Anita Playlot Playground Replacement | 24659 | Mike Del Campo | Installation of new play equipment at Santa Anita Playlot Playground to meet the needs of the community. |  | 2023-07-01 |  | 2025-03-01 | 2024-09-01 | City Council approved the project on 1/28/25. Pending paperwork from selected vendor.
13 | Burbank Channel Bikeway Public Art | 24558 | Megan Wilke | The project will design, construct and install up to seven public art pieces along the Burbank Channel Bikeway. | Planning | 2023-08-22 | On Hold | 2025-06-24 | 2025-06-01 | Call for Artists is anticipated by the end of FY 24/25. Staff is scheduling a meeting with Los Angeles County Flood Control District to discuss the project and receive feedback and approval.
14 | Johnny Carson Park Shade Structure | 24819 | Megan Wilke | Installation of a shade structure over the Johnny Carson Park stage. Parks and Recreation will coordinate structure locations with Public Works and will be plan checked and permitted by CDD/Building division. | Planning | 2023-07-23 | 2024-01-05 | 2025-09-30 | 2025-09-01 | Working with Purchasing and the Art Consultant on drafting RFQ. Purchasing is reviewing the final RFQ draft.
15
Legend:
On schedule
3 months behind
4+ months behind

## Completed FY23-24 (hidden)
Completed CIPs
FY 23/24
[6 empty] | Created in Oracle | Phase Schedule
| Project | Project Number | Project Manager | Scope | Phase | Project Start Date | Start | End | Construction Completion Date | Status
1 | Picnic Facility Improvements at Verdugo Park | 24214 | Mike Del Campo | Add new shade structure(s) to outdoor picnic areas to enhance the visitor's experience and provide increased safety from harmful ultraviolet (UV) radiation. Shade structures have the potential to generate additional revenue through permitted group gatherings and rentals. The Parks and Recreation Board has identified this project as a top priority. Additionally, the Department recently completed a series of community engagement workshops to determine the City's parks/facility needs where this was identified as a need by the community. Over 750 picnic facility reservations are scheduled each year. | Design | 2021-07-01 | 2023-07-21 | 2023-06-23 |  | Project Completed, June 2023
2 | DeBell Irrigation Improvements | 23859 | Mike Del Campo | Abandon in place all current irrigation and replace with modern updated water efficient irrigation using recycled water. | Construction | March 1 2022 | 2023-03-22 | 2023-08-22 |  | Project Completed, June 2023
3 | Whitnall Highway Park Fitness Equipment | 24563 | Mike Del Campo | Replacement of outdated fitness equipment at Whitnall Highway Park South. | Design-Build | 2022-12-01 | 2023-12-22 | 2023-05-23 |  | Project completed, May 2023.
4 | Police HQ/Fire 11 HVAC Retrofit and Repair | 23022 | Dean Pearson | This project will include system design, engineering, and construction. Funding will allow the replacement of some equipment to extend the service life of the HVAC equipment until the larger overall replacement project can be funded. | Construction | 2018-07-01 | 2023-05-22 | 2023-06-23 |  | COMPLETED and closing out.
5 | DeBell Golf Course Annual Improvements | 24561 | Mike Del Campo | Annual DeBell Golf Course improvements are required to maintain safe facility grounds while enhancing the quality of community recreation. Improvements include, but are not limited to: sand bunker renovation, course netting replacement, tree removal, tee level/widening, irrigation improvements, replacement of dirt cart paths to concrete, and the removal and replacement of netting at the driving range and perimeter of Golf Course. These improvements are necessary to increase the safety of players and overall community. Maintaining a safe and attractive facility for visitors and players is vital to the continued success of the DeBell Golf Course operations. Projects are outlined in a five year capital improvement program, and will occur in a phased plan approach. | On-Going | 2022-07-01 | 2023-07-22 | 2023-06-23 |  | Project Completed.
6 | Animal Shelter Shade Structure | 24562 | Kris Smith | This project will provide a new outside shade structure for Burbank Animal Shelter and shade covering for 50 kennels. | Design-Build | 2022-08-01 | 2023-08-22 | 2023-07-23 |  | Projected completed. August 2023.
7 | DeBell Irrigation Improvements | 23859 | Mike Del Campo | Abandon in place all current irrigation and replace with modern updated water efficient irrigation using recycled water. | Construction | March 1 2022 | 2023-03-22 | 2023-08-22 |  | Project Completed, June 2023
8 | Verdugo Aquatic Facility Public Art | 23432 | Paula Ohan | Funds will be used to develop a public mural for the Verdugo Aquatic Facility. | Design | 2023-07-19 | 2023-10-22 | 2023-12-22 |  | Project Completed, December 2022. However, the artist is adding a design element to include the newly added Sister City.
9 | Fiscal Year 21-22 Annual Arterial Pavement Rehabilitation | 24185 | Diana Reznik | The project will improve Victory Blvd from Clybourn Ave to Buena Vista St, San Fernando Road from south of Hollywood Way to north of Buena Vista St, and resurface the Burbank Fire Department Training Center parking lot. | Construction | 2023-07-21 | 2023-04-22 | 2023-07-23 |  | Waiting for two Change Orders to be approved to pay invoices and close project.
10 | Alameda Signal Synchronization | 23457 | David Wilcox | This project will synchronize 20 traffic signals on Alameda between Buena Vista and Glenoaks and on Riverside between Buena Vista and Chavez. The project is 100 percent funded by Metro Measure R Highway funds. | Design | 2023-02-20 | 2023-06-20 | 2023-06-23 |  | Design complete. Construction to occur with I-5 Project below.
11 | McCambridge 1 Ballfield Bleacher Shade Structure | 24556 | Diego Cevallos | Installation of cantilever ballfield bleacher shade structure at McCambridge softball field 1. Work to include design, engineering calculations, manufacturing of structure, and installation of a sheltered area over aluminum bleachers for program participants, employees, and the community to enjoy. | Design-Build | 2023-08-22 | 2023-08-22 | 2023-08-23 |  | Project Completed, October 2023.
12 | Park Playground Equipment and Replacement Valley and Ovrom Parks | 24213 | Mike Del Campo | New playgrounds/fitness equipment was the second highest prioritized project identified by the community. Playgrounds are an essential commodity in neighborhood parks and it is important to maintain the playgrounds to ensure longevity and safety. The Department keeps track of the installation dates of playgrounds to ensure that they are kept on a replacement cycle plan. Valley Park will receive a playground equipment replacement and installation of a new shade structure. The playground equipment and shade fabric at Ovrom Park will be replaced. | Design | 2023-07-21 | 2023-07-21 | 2023-11-23 |  | Construction at Ovrom Playground was completed June 2023. Construction at Valley Park Playground is anticipated to start September 2023 and is expected to be completed by November 2023. Valley Park Playground Construction began on August 30, 2023 and expected to be completed on October 20, 2023.
13 | Verdugo Water Slides | 24560 | Diego Cevallos | Application of gel coating of interior and exterior of two water slides. | Design-Build | 2023-07-22 | 2022-07-22 | 2023-08-23 |  | Project complete, will move to Completed tab. The work was anticipated to be completed by May 2023 in preparation for the summer 2023 season, but due to heavy rains this project was delayed. Project will start and be completed in August 2023 during the annual maintenance closure period. The PO was issued. This project will be completed December 2023.
14 | Ballfield Lighting Modernization at McCambridge 1 & 2 | 24557 | Mike Del Campo Diego Cevallos | Modernize ballfield lighting with energy efficient light emitting diode (LED) systems at McCambridge Fields 1 and 2. The existing eleven (11) light standards will also be replaced. The scope will include pre-cast concrete bases with integrated lighting grounding and light poles. | Design-Build | 2023-02-23 | 2023-02-23 | 2024-02-23 |  | P&R and PW are coordinated efforts on the project. The design has been completed. This Project started on December 4th. Ballfield #2 has been completed. Musco began work on ballfield #1 on January 8th. Construction was completed on February 7, 2024. A light survey was completed on February 12, 2024. NOC will be submitted after P&R and PW meet to closeout the project. Project is complete.
15 | Downtown San Fernando Blvd Reconfiguration (Phase 1) | 24206 | Edward Yu | This project reconfigures San Fernando Boulevard in Downtown Burbank to implement one lane of one-way traffic northbound, install signage, and modify roadway signal and striping, reconfigure parking, and add additional outdoor dining opportunities. If successful, a phase two project could be implemented to construct a long-term improvement with permanent wide sidewalks and traffic calming. | Phase 1 Complete | 2023-07-21 | 2024-02-24 | 2024-03-24 | 2024-03-24 | Phase 1 complete on March 8, 2024 . Conducting observations and evaluations of pilot program. Phase 2 will be created as a new project.
16 | Front St. Cycle Track Bike & Pedestrian Minor Project Improvements | 22377 | Vikki Davtian | The City's Bicycle Master Plan identifies a missing top priority safe bicycle connection from the Downtown Burbank Metrolink station to the Downtown Area. This project will design and construct approximately a half-mile protected Class IV bikeway along Front Street from the Downtown Burbank Metrolink station to Verdugo Avenue and South Ikea Way. This project is funded by Transportation Development Act (TDA) Article 3 and Measure R Local Return funds. | Construction | 2023-02-16 | 2024-03-31 | 2024-06-06 | 2024-05-24 | Project is complete.
17 | Schafer Ballfield Bleacher Shade Structure Installation | 24210 | Diego Cevallos | Installation of wrap around cantilever ballfield bleacher shade structure at Schafer field. Restricted BAF funds will be allocated to partially cover the costs of this project. | Construction | 2023-10-22 | 2022-10-22 | 2024-03-22 |  | Project completed, May 2024.
18 | McCambridge Recreation Center Gym Mural | 23433 | Megan Wilke | Funds will be used to develop a public mural for the McCambridge Recreation Center gymnasium. | Construction | 2023-07-19 | 2019-07-19 | 2024-05-01 | 2024-07-01 | Mural completed on May 10, 2024. Identification Plaque is in production.
19 | FY 23/24 Storm Drain Pump Station and Catch Basin Upgrades | 21310 | Steve Walker | This is a multi-year project is to implement capital improvements to the City's storm drain pump stations and catch basins/connector pipes, and related facilities. This project will improve the condition of storm drain facilities, thereby increasing the system reliability and reducing the chance of flooding during significant rain events. | Design/ Construct |  | 2023-07-01 | 2024-06-01 | 2024-06-01 | In FY 2023-24, new valves were installed and ventilation improvements were made at the Victory Place Storm Drain Pump Station; and a new sump pump and starter equipment was installed and pump motors were rehabilitated at the at the Hollywood Way & San Fernando Storm Drain Pump Station. In addition, the emergency project to remove and replace the deteriorated storm drain pipeline adjacent to the property at 5 West Magnolia Blvd. (Swaner Hardwood) was completed.