## NEW PW CDD FY24-25
Public Works and CDD CIPs
February 2025
[6 empty] | Created in Oracle | Phase Schedule
| Project | Project Number | Project Manager | Scope | Phase | Project Start Date | Start | End | Estimated Construction Completion Date | Status
New FY 24/25 Projects
37 | First Street Pocket Park | 24994 | Anthony Roman/Edward Yu | First Street Village project includes the development of a pocket park. City will partner with developer to fund construction cost. Developer will be responsible for maintenance costs of the park. |  |  |  | TBD | TBD | Developer to complete Pocket Park design by August 2024. Construction of pocket park is TBD based upon Developer schedule.
43 | FY 24/25 Annual Sidewalk Rehabilitation | 24949 | Frank Nerthling/ Sevak Hakobyan | The project will remove and reconstruct damaged curbs, gutters, sidewalks, driveways, and pedestrian ramps in Zones 1, 2, 19, 20. |  |  |  |  | 2026-09-01 | Working to determine the sidewalk segments and continue with design efforts | Cont'd
38 | FY 24/25 Annual Residential Pave Rehab (Phase IV of Cycle 2) | 24950 | Artin Megerdichian/ Frank Nerthling | FY 2024-25 will perform grind and overlay on streets in poor and below condition primarily in sections 13 and 14. |  |  |  |  | 2026-10-01 | Design 20% completed | Cont'd
44 | FY 2024-25 Annual Arterial Pavement Rehabilitation | 24951 | Frank Nerthling | The arterial pavement program continues to address major and secondary arterials and collector roadways rated poor and below condition to achieve a Citywide pavement condition index (PCI) of 73 by FY 2030-31. Combined with residential pavement program Public Works expects to achieve a citywide PCI of 73 by FY 2030-31. |  |  |  |  | 2026-11-01 | Working to determine the arterial segments and continue with design efforts | Cont'd
39 | Olive Avenue Bridge Replacement | 24975 | David Kriske / Marcos Fuentes/ Artin Megerdichian / Anna Hartounian | A feasibility study was completed in 2016 to potentially widen the Olive (and Magnolia) bridge. This project will update that study to determine the best rehabilitation strategy for the Olive Bridge as well as consider the new needs based upon Metro's upcoming implementation of the Bus Rapid Transit (BRT) line on Olive Avenue. |  |  |  |  | 2035-01-01 | Kick-off meeting held with PW and CDD to start the project. CDD takes the lead to release a RFP in late Jan. 2025 to select a consultant to update the 2016 Feasibility Report. The consultant will look at various rehab options including replacement of the bridge, perform outreach, and recommend funding options. | Cont'd
40 | FY 2024-25 Annual Facilities Small Capital Improvement | 24955 | Dean Pearson | Facility capital program/small capital planned and unplanned replacement/modernization/new building components, all aspects of facility related infrastructure such as; Interior building systems, electrical panels and lighting systems, HVAC, roofs and waterproofing systems, plumbing, and elevators. |  |  |  | 2024-06-25 | 2024-06-25 | Annual preparation of planned and unplanned small capital projects and programs have started. A summary of work completed in FY 23/24 and forecasted work in FY 24/25 is in process.
41 | PD Forensics Services Area Modernization | 24952 | Dean Pearson/Anna Hartounian | Renovate two existing areas: Forensic Services Laboratory & Administration areas and the Forensic Services Evidence Garage located on the facility's lower level. |  |  |  | 2024-06-27 | 27-Jun | Design is scheduled to be completed in April 2025. Building permit plancheck will start in May and be completed in July 2025. Construction will start in summer 2025/26 with either Co-op agreement or Bidding process(to be decided) and be completed in 2026/27.
42 | New EOC at City Hall | 24956 | Edward Yu/Damian Skinner | Renovate the northwest portion of City Hall's basement to construct a new City Emergency Operations Center (EOC). |  |  |  | 2024-02-26 | 2027-12-31 | PW gathering architectural information to provide to on-call architects for task order proposals. Begin selection of Architect spring 2025. Construction Completion by Spring 2027. Fire to obtain grant extension to June 2027. | Cont'd
45 | CAO Reconfiguration | 24982 | Jose Rodriguez | In addition to reorganizing 7 office areas, this project will also repurpose storage areas, modernize the existing lobby area to address safety and security concerns, and install a door from the City Attorney's Office storage vault into the copy room for direct access. | Construction | 2024-10-24 |  | 2025-05-01 | 2025-05-01 | Construction to start in Feb. 2025 and be completed by June 2025. Status: Phase 2 of the project to commence Feburary 18th. Project to be completed by May 2025. | Cont'd
46 | Community Services Building (CSB) Office Spaces | 25007 | Kenny Armenta | This project will split one office into two offices on the second floor of the CSB. Staff will procure a consultant to design the layout, build a drywall splitting the offices, add fire sprinklers, ceiling lights, and an additional wood door to the entrance. |  |  |  | 2024-08-25 | TBD | HMC Architects was selected for this project. Currently completing the PSA and City forms necessary to move forward with PSA. | Cont'd
Legend:
On schedule
3 months behind
4+ months behind

## NEW Parks FY24-25
Parks CIPs
February 2025
[6 empty] | Created in Oracle | Schedule
| Project | Project Number | Project Manager | Scope | Phase | Project Start Date | Start | End | Estimated Construction Completion Date (From CIP Sheets) | Status
New FY 24/25 Projects
15 | McCambridge Pool Replacement | 24979 | Diego Cevallos | Multi-phased renovation of the McCambridge Pool facility. Upgrades include a new lap swim pool, activity pool, waterslides, play features, pool deck, equipment room, and locker room renovations, and staff offices. | Planning | 2024-07-24 | 2024-07-01 | 2024-06-25 | 2028-06-01 | Design estimated completion date is July 2025. Phase 1 - Design development. Architects selected. PSA with architects being developed.
16 | Olive Park Ballfield Shade Structures on Fields 1, 2, 4 | 24976 | Diego Cevallos | Installation of cantilever bleacher shade structures at Olive Park Ballfield Diamonds 1, 2 & 4. | Planning | 2024-07-24 | 2024-07-01 | 2024-06-25 | 2025-06-01 | Co-op and proposal submitted to Purchasing for review on 8/15/24. Went to Council on December 17, 2024. Bonds submitted on 1/17/2025. Estimated construction start date is June 2025.
17 | Starlight Bowl Amphitheatre Transformation | 24980 | Kris Smith Edward Yu/Jose Rodriguez | The Starlight Bowl Amphitheatre Transformation Project consists of a complete renovation of the amphitheater with additional amenities to the site and adjacent facilities. | Planning | 2024-07-24 | 2024-09-09 | 2025-09-08 | 2025-06-01 | The project was presented to IDRC on 10/17/24 and 1/15/25 for feedback on the Preliminary Development Review. Arts and Community Engagement Consultants provided updates on 2/11/25 on Market Situation Analysis and community outeach efforts.
18 | Brace Canyon Park Playground Replacement | 24978 | Mike del Campo | Installation of new wide range inclusive and adaptive play equipment. | Planning | 2024-07-24 | 2024-10-24 | 2024-03-25 | 2025-06-01 | Construction began on 11/11/24. Anticipated completion date has been pushed to the end of April due to the completion of McCambridge Park playground and weather conditions.
Legend:
On schedule
3 months behind
4+ months behind

## Completed FY23-24 (hidden)
Completed CIPs
FY 23/24
[6 empty] | Created in Oracle | Phase Schedule
| Project | Project Number | Project Manager | Scope | Phase | Project Start Date | Start | End | Construction Completion Date | Status
1 | Picnic Facility Improvements at Verdugo Park | 24214 | Mike Del Campo | Add new shade structure(s) to outdoor picnic areas to enhance the visitor's experience and provide increased safety from harmful ultraviolet (UV) radiation. Shade structures have the potential to generate additional revenue through permitted group gatherings and rentals. The Parks and Recreation Board has identified this project as a top priority. Additionally, the Department recently completed a series of community engagement workshops to determine the City's parks/facility needs where this was identified as a need by the community. Over 750 picnic facility reservations are scheduled each year. | Design | 2021-07-01 | 2023-07-21 | 2023-06-23 |  | Project Completed, June 2023
2 | DeBell Irrigation Improvements | 23859 | Mike Del Campo | Abandon in place all current irrigation and replace with modern updated water efficient irrigation using recycled water. | Construction | March 1 2022 | 2023-03-22 | 2023-08-22 |  | Project Completed, June 2023
3 | Whitnall Highway Park Fitness Equipment | 24563 | Mike Del Campo | Replacement of outdated fitness equipment at Whitnall Highway Park South. | Design-Build | 2022-12-01 | 2023-12-22 | 2023-05-23 |  | Project completed, May 2023.
4 | Police HQ/Fire 11 HVAC Retrofit and Repair | 23022 | Dean Pearson | This project will include system design, engineering, and construction. Funding will allow the replacement of some equipment to extend the service life of the HVAC equipment until the larger overall replacement project can be funded. | Construction | 2018-07-01 | 2023-05-22 | 2023-06-23 |  | COMPLETED and closing out.
5 | DeBell Golf Course Annual Improvements | 24561 | Mike Del Campo | Annual DeBell Golf Course improvements are required to maintain safe facility grounds while enhancing the quality of community recreation. Improvements include, but are not limited to: sand bunker renovation, course netting replacement, tree removal, tee level/widening, irrigation improvements, replacement of dirt cart paths to concrete, and the removal and replacement of netting at the driving range and perimeter of Golf Course. These improvements are necessary to increase the safety of players and overall community. Maintaining a safe and attractive facility for visitors and players is vital to the continued success of the DeBell Golf Course operations. Projects are outlined in a five year capital improvement program, and will occur in a phased plan approach. | On-Going | 2022-07-01 | 2023-07-22 | 2023-06-23 |  | Project Completed.
6 | Animal Shelter Shade Structure | 24562 | Kris Smith | This project will provide a new outside shade structure for Burbank Animal Shelter and shade covering for 50 kennels. | Design-Build | 2022-08-01 | 2023-08-22 | 2023-07-23 |  | Projected completed. August 2023.
7 | DeBell Irrigation Improvements | 23859 | Mike Del Campo | Abandon in place all current irrigation and replace with modern updated water efficient irrigation using recycled water. | Construction | March 1 2022 | 2023-03-22 | 2023-08-22 |  | Project Completed, June 2023
8 | Verdugo Aquatic Facility Public Art | 23432 | Paula Ohan | Funds will be used to develop a public mural for the Verdugo Aquatic Facility. | Design | 2023-07-19 | 2023-10-22 | 2023-12-22 |  | Project Completed, December 2022. However, the artist is adding a design element to include the newly added Sister City.
9 | Fiscal Year 21-22 Annual Arterial Pavement Rehabilitation | 24185 | Diana Reznik | The project will improve Victory Blvd from Clybourn Ave to Buena Vista St, San Fernando Road from south of Hollywood Way to north of Buena Vista St, and resurface the Burbank Fire Department Training Center parking lot. | Construction | 2023-07-21 | 2023-04-22 | 2023-07-23 |  | Waiting for two Change Orders to be approved to pay invoices and close project.
10 | Alameda Signal Synchronization | 23457 | David Wilcox | This project will synchronize 20 traffic signals on Alameda between Buena Vista and Glenoaks and on Riverside between Buena Vista and Chavez. The project is 100 percent funded by Metro Measure R Highway funds. | Design | 2023-02-20 | 2023-06-20 | 2023-06-23 |  | Design complete. Construction to occur with I-5 Project below.
11 | McCambridge 1 Ballfield Bleacher Shade Structure | 24556 | Diego Cevallos | Installation of cantilever ballfield bleacher shade structure at McCambridge softball field 1. Work to include design, engineering calculations, manufacturing of structure, and installation of a sheltered area over aluminum bleachers for program participants, employees, and the community to enjoy. | Design-Build | 2023-08-22 | 2023-08-22 | 2023-08-23 |  | Project Completed, October 2023.
12 | Park Playground Equipment and Replacement Valley and Ovrom Parks | 24213 | Mike Del Campo | New playgrounds/fitness equipment was the second highest prioritized project identified by the community. Playgrounds are an essential commodity in neighborhood parks and it is important to maintain the playgrounds to ensure longevity and safety. The Department keeps track of the installation dates of playgrounds to ensure that they are kept on a replacement cycle plan. Valley Park will receive a playground equipment replacement and installation of a new shade structure. The playground equipment and shade fabric at Ovrom Park will be replaced. | Design | 2023-07-21 | 2023-07-21 | 2023-11-23 |  | Construction at Ovrom Playground was completed June 2023. Construction at Valley Park Playground is anticipated to start September 2023 and is expected to be completed by November 2023. Valley Park Playground Construction began on August 30, 2023 and expected to be completed on October 20, 2023.
13 | Verdugo Water Slides | 24560 | Diego Cevallos | Application of gel coating of interior and exterior of two water slides. | Design-Build | 2023-07-22 | 2022-07-22 | 2023-08-23 |  | Project complete, will move to Completed tab. The work was anticipated to be completed by May 2023 in preparation for the summer 2023 season, but due to heavy rains this project was delayed. Project will start and be completed in August 2023 during the annual maintenance closure period. The PO was issued. This project will be completed December 2023.
14 | Ballfield Lighting Modernization at McCambridge 1 & 2 | 24557 | Mike Del Campo Diego Cevallos | Modernize ballfield lighting with energy efficient light emitting diode (LED) systems at McCambridge Fields 1 and 2. The existing eleven (11) light standards will also be replaced. The scope will include pre-cast concrete bases with integrated lighting grounding and light poles. | Design-Build | 2023-02-23 | 2023-02-23 | 2024-02-23 |  | P&R and PW are coordinated efforts on the project. The design has been completed. This Project started on December 4th. Ballfield #2 has been completed. Musco began work on ballfield #1 on January 8th. Construction was completed on February 7, 2024. A light survey was completed on February 12, 2024. NOC will be submitted after P&R and PW meet to closeout the project. Project is complete.
15 | Downtown San Fernando Blvd Reconfiguration (Phase 1) | 24206 | Edward Yu | This project reconfigures San Fernando Boulevard in Downtown Burbank to implement one lane of one-way traffic northbound, install signage, and modify roadway signal and striping, reconfigure parking, and add additional outdoor dining opportunities. If successful, a phase two project could be implemented to construct a long-term improvement with permanent wide sidewalks and traffic calming. | Phase 1 Complete | 2023-07-21 | 2024-02-24 | 2024-03-24 | 2024-03-24 | Phase 1 complete on March 8, 2024 . Conducting observations and evaluations of pilot program. Phase 2 will be created as a new project.
16 | Front St. Cycle Track Bike & Pedestrian Minor Project Improvements | 22377 | Vikki Davtian | The City's Bicycle Master Plan identifies a missing top priority safe bicycle connection from the Downtown Burbank Metrolink station to the Downtown Area. This project will design and construct approximately a half-mile protected Class IV bikeway along Front Street from the Downtown Burbank Metrolink station to Verdugo Avenue and South Ikea Way. This project is funded by Transportation Development Act (TDA) Article 3 and Measure R Local Return funds. | Construction | 2023-02-16 | 2024-03-31 | 2024-06-06 | 2024-05-24 | Project is complete.
17 | Schafer Ballfield Bleacher Shade Structure Installation | 24210 | Diego Cevallos | Installation of wrap around cantilever ballfield bleacher shade structure at Schafer field. Restricted BAF funds will be allocated to partially cover the costs of this project. | Construction | 2023-10-22 | 2022-10-22 | 2024-03-22 |  | Project completed, May 2024.
18 | McCambridge Recreation Center Gym Mural | 23433 | Megan Wilke | Funds will be used to develop a public mural for the McCambridge Recreation Center gymnasium. | Construction | 2023-07-19 | 2019-07-19 | 2024-05-01 | 2024-07-01 | Mural completed on May 10, 2024. Identification Plaque is in production.
19 | FY 23/24 Storm Drain Pump Station and Catch Basin Upgrades | 21310 | Steve Walker | This is a multi-year project is to implement capital improvements to the City's storm drain pump stations and catch basins/connector pipes, and related facilities. This project will improve the condition of storm drain facilities, thereby increasing the system reliability and reducing the chance of flooding during significant rain events. | Design/ Construct |  | 2023-07-01 | 2024-06-01 | 2024-06-01 | In FY 2023-24, new valves were installed and ventilation improvements were made at the Victory Place Storm Drain Pump Station; and a new sump pump and starter equipment was installed and pump motors were rehabilitated at the at the Hollywood Way & San Fernando Storm Drain Pump Station. In addition, the emergency project to remove and replace the deteriorated storm drain pipeline adjacent to the property at 5 West Magnolia Blvd. (Swaner Hardwood) was completed.